## Open
| Last Extract: | 2023-05-04 20:10
Notification | Author | Required Start | Required End | Description | Task Status | Task number | Task code text | Task text | DescEmployeeResp.for job | Planned start date | Planned finish | Changed On | Time of change | DM Age
201352340 | Anuksha Manoj Jaju | 2023-04-18 | 2023-05-05 |  | TSRL REQ | 4 | Perform Independent Check | Perform Peer Review | Gouthami Jagga | 2023-05-03 | 2023-05-04 | 2023-05-03 | 16:48 | 1238
201353834 | Bekkam Rajashekar | 2023-04-20 | 2023-05-05 |  | TSRL REQ | 1 | DCF Task | Awaiting confirmation from site | Mahesh Ommi | 2023-04-20 | 2023-05-05 | 2023-04-27 | 18:54 | 1236
201354293 | Chiranjeevi Bollini | 2023-04-21 | 2023-05-05 |  | TSRL REQ | 1 | DCF Task | Awaiting for Master data confirmation | Mamatha Sadineni | 2023-04-21 | 2023-05-05 | 2023-04-28 | 18:11 | 1235
201357835 | Dande Reddy | 2023-05-02 | 2023-05-09 |  | TSRL REQ | 3 | Maintain Master Data | 5 GTIN Setup SLT | Manisha Goski | 2023-05-02 | 2023-05-04 | 2023-05-02 | 20:59 | 1224
201357814 | Gouthami Jagga | 2023-05-02 | 2023-05-09 |  | TSRL REQ | 4 | Perform Independent Check | Perform Peer Review | Ramya Kodamanchili | 2023-05-04 | 2023-05-05 | 2023-05-03 | 21:45 | 1224
201357820 | Mahesh Ommi | 2023-05-03 | 2023-05-09 |  | TSRL REQ | 3 | Maintain Master Data | 21 GTIN setup,see long text | Rizwan Ul Hasan Siddiqui | 2023-05-03 | 2023-05-05 | 2023-05-03 | 10:49 | 1223
201358099 | Mamatha Sadineni | 2023-05-03 | 2023-05-09 |  | TSRL REQ | 4 | Perform Independent Check | Perform peer review | Sandeep Kumar | 2023-05-04 | 2023-05-05 | 2023-05-04 | 7:53 | 1223
201357884 | Manisha Goski | 2023-05-03 | 2023-05-09 |  | TSRL REQ | 3 | Maintain Master Data | 1 Partial Batch Decomm, see long text | Sravya Reddy | 2023-05-04 | 2023-05-08 | 2023-05-04 | 14:11 | 1223
201357586 | Naraparaju Manasa | 2023-05-02 | 2023-05-09 |  | TSRL REQ | 8 | Complete Notification & Inform Requestor | Informed requestor | Sriram Podicheti | 2023-05-03 | 2023-05-09 | 2023-05-03 | 21:01 | 1224
201357675 | Rahul Nesarikar | 2023-05-02 | 2023-05-09 |  | TSRL REQ | 8 | Complete Notification & Inform Requestor | Informed requestor | Tamarala Sisindri | 2023-05-04 | 2023-05-09 | 2023-05-04 | 10:58 | 1224
201357932 | Ramya Kodamanchili | 2023-05-03 | 2023-05-09 |  | TSRL REQ | 8 | Complete Notification & Inform Requestor | Informed requestor | Naraparaju Manasa | 2023-05-04 | 2023-05-09 | 2023-05-04 | 14:34 | 1223
201358095 | Rizwan Ul Hasan Siddiqui | 2023-05-03 | 2023-05-10 |  | TSRL REQ | 2 | QA Approval Required to Proceed? | Approval task | Rahul Nesarikar | 2023-05-03 | 2023-05-04 | 2023-05-03 | 15:07 | 1223
201358307 | Sandeep Kumar | 2023-05-03 | 2023-05-10 |  | TSRL REQ | 3 | Maintain Master Data | 1 Partial Batch Decomm, see long text | Sandeep Kumar | 2023-05-04 | 2023-05-08 | 2023-05-04 | 13:21 | 1223
201358504 | Sravya Reddy | 2023-05-04 | 2023-05-10 |  | TSRL REQ | 1 | DCF Task | Checking DRF | Anuksha Manoj Jaju | 2023-05-04 | 2023-05-08 | 2023-05-04 | 10:37 | 1222
201358725 | Sriram Podicheti | 2023-05-04 | 2023-05-10 |  | TSRL REQ | 1 | DCF Task | N/A DATA PROVIDED IN DCF | Bekkam Rajashekar | 2023-05-04 | 2023-05-08 | 2023-05-04 | 14:25 | 1222
201358396 | Suneerunnisa Begum | 2023-05-04 | 2023-05-10 |  | TSOS REQ | 3 | Maintain Master Data | Partial batch decomm, see long text | Chiranjeevi Bollini | 2023-05-04 | 2023-09-04 |  | 0:00 | 1222
201358691 | Tamarala Sisindri | 2023-05-04 | 2023-05-11 |  | TSRL REQ | 3 | Maintain Master Data | 1 Full Batch Decomm, see long text | Dande Reddy | 2023-05-04 | 2023-05-08 | 2023-05-04 | 13:53 | 1222
201358536 | Naraparaju Manasa | 2023-05-04 | 2023-05-11 |  | TSRL REQ | 4 | Perform Independent Check | Perform Peer Review | Rizwan Ul Hasan Siddiqui | 2023-05-04 | 2023-05-11 | 2023-05-04 | 12:07 | 1222
201329758 | Rahul Nesarikar | 2023-02-23 | 2023-05-15 |  | TSRL REQ | 1 | DCF Task | Awaiting confirmation from Harshal | Sandeep Kumar | 2023-02-23 | 2023-05-15 | 2023-04-28 | 5:14 | 1292
201358351 | Sandeep Kumar | 2023-05-03 | 2023-05-19 |  | TSRL REQ | 2 | QA Approval Required to Proceed? | Approval task | Sravya Reddy | 2023-05-03 | 2023-05-19 | 2023-05-03 | 17:06 | 1223
Formulas:
DM Age = INT(TODAY()-[Required Start]+(1))

## Productivity
P R O D U C T I V I T Y T R A C K E R |  |  | S u m M T D
January
MUD ID | Name | Category | DM | Task
am427825 | Anuksha Manoj Jaju | DM / Russia / Saudi
br690118 | Bekkam Rajashekar | DM / Alerts / US
cb832551 | Chiranjeevi Bollini | DM / Vx
dvr95541 | Dande Reddy | DM / Error Monitoring & Reporting
gsj65824 | Gouthami Jagga | DM / Phase 1
om209107 | Mahesh Ommi | DM / Error Monitoring & Reporting
ms550164 | Mamatha Sadineni | Training
mg104360 | Manisha Goski | DM / Phase 2 & ELS Saudi
nm846496 | Naraparaju Manasa | DM / Vx / Error Monitoring & Reporting
rn545895 | Rahul Nesarikar | DM / Russia / DV
rk440576 | Ramya Kodamanchili | Training
rh294814 | Rizwan Ul Hasan Siddiqui | DM / Russia / Saudi
spk12633 | Sandeep Kumar | Alerts / ELS Saudi / Vx
sr463655 | Sravya Reddy | DM / Error Monitoring & Reporting
sp128618 | Sriram Podicheti | Training
sb641236 | Suneerunnisa Begum | Phase 1 / Process Documents
txs21997 | Tamarala Sisindri | Training
|  | Total | 0 | 0